## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Bob Smith | 555-5676 | 8 | Mon - Fri
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Sue Jones
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWCoffeeMerchant | Data Warehouse | CoffeeMerchant OLTP | Database | Database
DWCoffeeMerchant.dbo.FactSales | Fact Table | CoffeeMerchant.dbo.Sales | Table | Table
DWCoffeeMerchant.dbo.Date-SK | Dimension Key Column | CoffeeMerchant.dbo.order.orderdate | datetime | datetime
DWCoffeeMerchant.dbo.Consumer-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.Inventory-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.Employee-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.FactSales.InventoryPrice | Measure Column | CoffeeMerchant.dbo.Inventory.Price | numeric(6,2) | numeric(6,2)
DWCoffeeMerchant.dbo.FactSales.Quantity | Measure Column | CoffeeMerchant.dbo.OrderLine.Quantity | int | int
DWCoffeeMerchant.dbo.FactSales.Discount | Measure Column | CoffeeMerchant.dbo.OrderLine.Discount | numeric(4,4) | numeric(4,4)
DWCoffeeMerchant.dbo.DimConsumer | Dimesion Table | CoffeeMerchant.dbo.consumer | Table | Table
DWCoffeeMerchant.dbo.DimConsumer.ConsumerKey-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimConsumer.ConsumerId-AK | Dimension Key Column | CoffeeMerchant.dbo.consumer.consumer_id | int | int
DWCoffeeMerchant.dbo.DimConsumer.ConsumerState | Dimension Column | CoffeeMerchant.dbo.consumer.state | nvarchar(2) | nvarchar(2)
DWCoffeeMerchant.dbo.DimConsumer.ConsumerCity | Dimension Column | CoffeeMerchant.dbo.consumer.city | nvarchar(50) | nvarchar(50)
DWCoffeeMerchant.dbo.DimConsumer.ConsumerZipcode | Dimension Column | CoffeeMerchant.dbo.consumer.zipcode | nvarchar(11) | nvarchar(11)
DWCoffeeMerchant.dbo.DimConsumer.ConsumerCreditLimit | Dimension Column | CoffeeMerchant.dbo.consumer.creditlimit | int | int
DWCoffeeMerchant.dbo.DimInventory | Dimesion Table | CoffeeMerchant.dbo.inventory | Table | Table
DWCoffeeMerchant.dbo.DimInventory.InventoryKey-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimInventory.InventoryId | Dimension Key Column | CoffeeMerchant.dbo.inventory.inventory_id | int | int
DWCoffeeMerchant.dbo.DimInventory.Name | Dimension Column | CoffeeMerchant.dbo.inventory.name | nvarchar(40) | nvarchar(40)
DWCoffeeMerchant.dbo.DimInventory.ItemType | Dimension Column | CoffeeMerchant.dbo.inventory.item_type | nvarchar(5) | nvarchar(5)
DWCoffeeMerchant.dbo.DimInventory.Country | Dimension Column | CoffeeMerchant.dbo.country.country_name | nvarchar(40) | nvarchar(40)
DWCoffeeMerchant.dbo.DimEmployee | Dimesion Table | CoffeeMerchant.dbo.employee | Table | Table
DWCoffeeMerchant.dbo.DimEmployee.EmployeeKey-SK | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimEmployee.EmployeeId-AK | Dimension Key Column | CoffeeMerchant.dbo.employee.employee_id | int | int
DWCoffeeMerchant.dbo.DimEmployee.LastName | Dimension Column | CoffeeMerchant.dbo.employee.last_name | nvarchar(30) | nvarchar(30)
DWCoffeeMerchant.dbo.DimEmployee.ComissionRate | Dimension Column | CoffeeMerchant.dbo.employee.comission_rate | numeric(4,4) | numeric(4,4)
DWCoffeeMerchant.dbo.DimEmployee.HireDate | Dimension Column | CoffeeMerchant.dbo.employee.hire_date | datetime | datetime
DWCoffeeMerchant.dbo.DimEmployee.BirthDate | Dimension Column | CoffeeMerchant.dbo.employee.birthdate | datetime | datetime
DWCoffeeMerchant.dbo.DimEmployee.Gender | Dimension Column | CoffeeMerchant.dbo.employee.gender | nvarchar(1) | nvarchar(1)
DWCoffeeMerchant.dbo.DimDates | Dimesion Table | na | na | Table
DWCoffeeMerchant.dbo.DimDates.Date_SK | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDates.DateName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDates.Month | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDates.MonthName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDates.Quarter | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDates.QuarterName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDates.Year | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDates.YearName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDates.Holiday | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDates.HolidayName | Dimension Column | na | na | nvarchar(50)
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description